## OpenCart_Bug_Report
Test Case ID | Test Scenario | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Priority | Test Type
OPC-REG_01_05 | Register with special characters in name | Navigate to registration - Use special characters in First/Last Name | First: John$, Last: D@e | Registration should fail Error message should be shown near the name fields | Registration succeeded. No error message displayed. User redirected to account/success page. | Fail | High | High | Negative
OPC-REG_01_07 | Register with password length 21 | Navigate to registration - Use password length 21 | a*21 | Registration should fail Error message should be shown near the password field | Registration succeeded. No error message displayed. User redirected to account/success page | Fail | High | High | Negative
OPC-CHK_05_04 | Edit cart quantity and complete checkout | 1. Add product to cart 2. Edit quantity 3. Proceed to checkout | Quantity: 2 | Shipping method section should appear and allow the user to continue | Shipping method button not found. Checkout blocked. TimeoutException raised | Fail | Critical | High | Functional